## Item Lists
DARBO DRIVE TO WEBB AVENUE NEW STREET CONNECTION ASSESSMENT DISTRICT - 2018 (RICHARD DAVIS LANE)
CONTRACT NO. 7450
DATE: 5/24/18
|  | Speedway Sand & Gravel, Inc. |  | R.G. Huston Co., Inc.
Item | Quantity | Price | Extension | Price | Extension
Section B: Proposal Page
10701.0 - TRAFFIC CONTROL - LUMP SUM | 1 | 4828 | 4828 | 4828 | 4828
10720.0 - TRAFFIC CONTROL SIGN - PORTABLE ARROW BOARD - DAYS | 14 | 25 | 350 | 25 | 350
10911.0 - MOBILIZATION - LUMP SUM | 1 | 75700 | 75700 | 122500 | 122500
20101.0 - EXCAVATION CUT - C.Y. | 2125 | 22.5 | 47812.5 | 30.5 | 64812.5
20130.0 - UNDERDRAIN - L.F. | 553 | 15 | 8295 | 20 | 11060
20140.0 - GEOTEXTILE FABRIC TYPE SAS (NON-WOVEN) - S.Y. | 454 | 2.65 | 1203.1 | 1.3 | 590.2
20219.0 - BREAKER RUN - TON | 757 | 14 | 10598 | 11.75 | 8894.75
20221.0 - TOPSOIL - S.Y. | 3425 | 6.05 | 20721.25 | 7.8 | 26715
20303.0 - SAWCUT ASPHALT PAVEMENT - L.F. | 484 | 2.5 | 1210 | 1.25 | 605
20321.0 - REMOVE CONCRETE PAVEMENT - S.Y. | 69 | 18 | 1242 | 16 | 1104
20322.0 - REMOVE CONCRETE CURB & GUTTER - L.F. | 312 | 3.5 | 1092 | 5.15 | 1606.8
20323.0 - REMOVE CONCRETE SIDEWALK AND DRIVE - S.F. | 995 | 2.25 | 2238.75 | 4.65 | 4626.75
20401.0 - CLEARING - I.D. | 55 | 60 | 3300 | 60 | 3300
20406.0 - GRUBBING - I.D. | 55 | 60 | 3300 | 60 | 3300
20701.0 - TERRACE SEEDING - S.Y. | 3425 | 1.55 | 5308.75 | 2 | 6850
21063.0 - EROSION MATTING, CLASS I, TYPE A - ORGANIC - S.Y. | 3425 | 1.75 | 5993.75 | 3 | 10275
30201.0 - TYPE "A" CONCRETE CURB & GUTTER - L.F. | 1074 | 17 | 18258 | 25.25 | 27118.5
30206.0 - TYPE "G" CONCRETE CURB & GUTTER - L.F. | 348 | 18 | 6264 | 25.25 | 8787
30208.0 - HAND FORMED CONCRETE CURB & GUTTER - L.F. | 20 | 28 | 560 | 46.46 | 929.2
30301.0 - 5 INCH CONCRETE SIDEWALK - S.F. | 1007 | 6 | 6042 | 6.7 | 6746.9
30302.0 - 7 INCH CONCRETE SIDEWALK & DRIVE - S.F. | 826 | 7 | 5782 | 7.8 | 6442.8
30340.0 - CURB RAMP DETECTABLE WARNING FIELDS - S.F. | 56 | 40 | 2240 | 32.32 | 1809.92
40101.0 - CRUSHED AGGREGATE BASE COURSE, GRADATION NO. 1 - TON | 835 | 17 | 14195 | 15.6 | 13026
40102.0 - CRUSHED AGGREGATE BASE COURSE, GRADATION NO. 2 - TON | 1057 | 6 | 6342 | 18.8 | 19871.6
40202.0 - HMA PAVEMENT 4 LT 58-28S - TON | 487 | 67.42 | 32833.54 | 67.42 | 32833.54
40211.0 - TACK COAT - GAL | 231 | 3.03 | 699.93 | 3.03 | 699.93
40231.0 - ASPHALT DRIVE AND TERRACE - S.Y. | 50 | 18.18 | 909 | 47.65 | 2382.5
40410.0 - CONCRETE SPEED HUMP - S.Y. | 69 | 85 | 5865 | 92.93 | 6412.17
60421.0 - REMOVE STREET LIGHT BASE - EACH | 1 | 750 | 750 | 500 | 500
90001.0 - OBLITERATING PARKING LOT - S.Y. | 3923 | 3 | 11769 | 1.3 | 5099.9
90002.0 - TEMPORARY FENCING - LF | 920 | 4.5 | 4140 | 4.85 | 4462
50401.0 - 12 INCH TYPE I RCP STORM SEWER PIPE - L.F. | 56 | 78.61 | 4402.16 | 110 | 6160
50432.0 - 12 INCH TYPE II PAVEMENT STORM SEWER PIPE - L.F. | 133 | 78.61 | 10455.13 | 110 | 14630
50443.0 - 12 INCH TYPE III STORM SEWER PIPE - L.F. | 26 | 78.61 | 2043.86 | 110 | 2860
50741.0 - TYPE H INLET - EACH | 9 | 2959 | 26631 | 2700 | 24300
50761.0 - SADDLED INLET TYPE I - EACH | 2 | 3959 | 7918 | 3485 | 6970
20217.0 - CLEAR STONE - TON | 200 | 7 | 1400 | 11.85 | 2370
20313.0 - REMOVE INLET - EACH | 3 | 500 | 1500 | 500 | 1500
20314.0 - REMOVE PIPE - LF | 43 | 30 | 1290 | 45.65 | 1962.95
21002.0 - EROSION CONTROL INSPECTION - EACH | 3 | 550 | 1650 | 550 | 1650
21011.0 - CONSTRUCTION ENTRANCE - EACH | 1 | 300 | 300 | 550 | 550
21012.0 - STREET CONSTRUCTION ENTRANCE BERM - EACH | 1 | 300 | 300 | 325 | 325
21013.0 - STREET SWEEPING - LUMP SUM | 1 | 4000 | 4000 | 800 | 800
21017.0 - SILT SOCK (8 INCH) COMPLETE - LF | 160 | 8 | 1280 | 8 | 1280
21042.0 - INLET PROTECTION TYPE D - PROVIDE & INSTALL - EACH | 15 | 180 | 2700 | 180 | 2700
21043.0 - INLET PROTECTION TYPE D - MAINTAIN - EACH | 15 | 80 | 1200 | 80 | 1200
21044.0 - INLET PROTECTION TYPE D - REMOVE - EACH | 15 | 60 | 900 | 60 | 900
50202.0 - TYPE II DEWATERING - LUMP SUM | 1 | 500 | 500 | 390 | 390
50211.0 - SELECT BACKFILL FOR STORM SEWER - T.F. | 761 | 1 | 761 | 0.01 | 7.61
50461.0 - 12 INCH RCP AE - EACH | 1 | 871 | 871 | 930 | 930
50601.0 - 12 INCH RCP AE GATE - EACH | 1 | 442 | 442 | 370 | 370
50792.0 - STORM SEWER TAP - EACH | 7 | 1500 | 10500 | 1700 | 11900
50801.0 - UTILITY LINE OPENING - EACH | 2 | 700 | 1400 | 960 | 1920
21014.0 - CLEAR STONE BERM (DITCH CHECK) - EACH | 1 | 200 | 200 | 550 | 550
50780.0 - 6" PVC CLEAN OUT WITH SCREW CAP - EACH | 2 | 300 | 600 | 525 | 1050
90040.0 - ENGINEERED FILL - CY | 14.81 | 60 | 888.6 | 52 | 770.12
90041.0 - WASHED PEA GRAVEL - TON | 3 | 100 | 300 | 75 | 225
90042.0 - FLEXIBLE PIPE CONNECTOR - EACH | 1 | 2300 | 2300 | 2350 | 2350
90043.0 - GEOTEXTILE FABRIC AND PLACEMENT - SF | 1200 | 1 | 1200 | 4.5 | 5400
60229.0 - FURNISH & INSTALL 2 INCH PVC (SCHEDULE 80) CONDUIT BY "OPEN TRENCH" METHOD - LF | 113 | 25 | 2825 | 25 | 2825
60231.0 - FURNISH & INSTALL 2 INCH PVC (SCHEDULE 40) CONDUIT BY "OPEN TRENCH" METHOD - LF | 478 | 18 | 8604 | 18 | 8604
60427.0 - REMOVE ELECTRICAL HANDHOLE - EACH | 1 | 300 | 300 | 300 | 300
60702.0 - CONSTRUCT ELECTRICAL HANDHOLE TYPE 1 - EACH | 4 | 1500 | 6000 | 1500 | 6000
60704.0 - CONSTRUCT ELECTRICAL HANDHOLE TYPE 3 - EACH | 2 | 1000 | 2000 | 1000 | 2000
20233.0 - RIPRAP FILTER FABRIC, TYPE HR - S.Y. | 485 | 5 | 2425 | 3.25 | 1576.25
90031.0 - REMOVE TRANSITION - LUMP SUM | 1 | 2500 | 2500 | 3500 | 3500
90032.0 - 4'X18' STRUCTURE - EACH | 1 | 63000 | 63000 | 13800 | 13800
90033.0 - 8'X4' ASTM-C-1433 STORM BOX - L.F. | 546 | 860 | 469560 | 819 | 447174
90034.0 - STORM CONTROL PLAN AND IMPLEMENTATION - LUMP SUM | 1 | 20000 | 20000 | 500 | 500
69 Items | Totals |  | 974989.32 | 990839.89